## Sheet1
S.No | Major Tasks | Breakdown Tasks | Completion% | Assigned to | Planned Start Date | Planned End Date | Comment
1 | Analysis of the WiPDM usage | NA | 100 | Inderajith | 4.12.2018 | 5.12.2018 | WiPDM will be needed after XML generation for tranform
2 | Clorox Datamodel Analysis | NA | 100 | Sivaranjani | 4.12.2018 | 5.12.2018
3 | Data Modelling/Other Tasks | Material & Substance datamodel | 50 | Inderajith | 5.12.2018 | NA
|  | SSO Analysis | 100 | Inderajith | 6.12.2018 | 7.12.2018
|  | Spinners Installation | 100 | Inderajith | 11.12.2018 | 11.12.2018
3 | SAP PDM Extract Analysis | Sample XML creation | 50 | Inderajith | 4.12.2018 | NA
|  | Specification Extract format | 20 | Inderajith | 11.12.2018 | NA
Recipes Extract format
ECM Extract format
Mapping to 3DX
4 | Lotus Notes Raw material data Extract Analysis | Sample XML creation | 50 | Inderajith
Raw material Data Extract format
Mapping to 3DX
5 | Migration Tool Development | XML Transform for single data - SAP PDM
XML Transform for BOM data - SAP PDM
XML Transform for single raw material data - Lotus
XML Transform for whole raw material data - Lotus
SAP PDM Loading - single data
SAP PDM Loading - BOM data
Raw Data Loading - single data
Raw Data Loading - whole data
6 | Document Migration | Document extract format analysis
Document migration coding
Document Loading
7 | Data Migration Design document | NA |  | Inderajith