## Alchemy
Class/Type | Subclass/SubType | Completion % on Specification template and parts | PLM |  |  | STEP |  |  | Integrations | Data Migration
|  |  | Activities for each Type | Activities for each SubType | Other | Activities for each Type | Activities for each SubType | Other
Pallet Part |  | 100 | Identify subtypes |  | Identify characteristics category | Develop Assets, Classifications, Entities , Hierarchies, Attributes , Lookups , taxonomies, Cross References (STEP)
| Full Pallet |  | Identify attributes | Identify attributes | Identify characteristics | Develop data integration, Conversion routines, Publications (STEP)
| Half Pallet |  | Identify specification templates | Identify specification templates | Identify test methods per characteristic | Develop data syndication/import mappings/routines (STEP)
| Quarter Pallet |  | Identify sections | Identify sections | Identify document types | Develop data syndication/Export mappings/routines (STEP)
Trade Unit Part |  |  | Identify attributes by sections | Identify attributes by sections | Identify document type hierarchy | Develop data management workflows (STEP)
Consumer Unit Part |  |  |  | Identify data import template | Attach Supplier/MEP | Develop data management web user interface (STEP)
Packaging Component |  | 56 |  |  | Create EBOM | Develop data Bulk uploads/updates/Data Migration from legacy systems (STEP)
| Aerosol Valve |  |  |  | Create MBOM | Develop Data Profiling, Data Score Containers & Business rules (STEP)
| Bag |  |  |  | Create FBOM | Develop External Data Enrichment Processes flows
| Box |  |  |  |  | Develop data score metrics dashboard user interface (STEP)
| Cap |  |  |  |  | Finalize and Build Reference Data (List of Values)
| Tote Bin |  |  |  |  | Configure Data Score Containers (STEP)
| Bottle |  |  |  |  | Develop User Interface for Data Management (STEP)
| Bucket Drum Lid |  |  |  |  | Enable Match, Merge and Linking algorithms (STEP)
| Can |  |  |  |  | Develop Reports and related Universe (STEP)
| Carton |  |  |  |  | Configuration of User, Role, Access Control (SAML Integration) setup for STEP Tool
Case
Closure
Display Components
Unit Load Packaging
Flexible Packaging
Hardware
Instructions/Brochures
Labels
Miscellaneous
Molded Component
Partitions
Packaging Assemblies
Triggers/Pumps
Thermoforms
Tube
Case Packaging Component Part
Packaging Material Part
Formulation Part
Raw Material
Acids
Bases
Salts
Flexible
Foods
Fragrances
Liquids
Solids
Mixtures
Substance
Label Part

## Specification Management
Sl.No | Type | Entity | Task | Owner | Status | Completeion % | Comments
1 |  | Characteristric Master | Create Characteristics |  |  |  | Define Characteristics Master needed for each data type below.
Create Template
Package Spec Types
1 | Pallet Pack Components | Full Pallet |  | Vipin | Completed | 100
Create Attributes
|  |  | Create Template |  |  |  | Template: CLX-Pallet
|  |  | Define Characteristic Criteria |  |  |  | Configured on part level
|  | Half Pallet |  | Vipin | Completed | 100
Create Attributes
|  |  | Create Template |  |  |  | Template: Pallet-1/2Pallet-Template
|  |  | Define Characteristic Criteria |  |  |  | Configured on part level
|  | Quarter Pallet |  | Vipin | Completed | 100
Create Attributes
|  |  | Create Template |  |  |  | Template: Pallet-1/4Pallet-Template
|  |  | Define Characteristic Criteria |  |  |  | Configured on part level
2 |  | Bottles |  | Vipin | Completed | 100
|  |  | Create Attributes |  |  |  | Template: CLX Bottle Template
|  |  | Create Template |  |  |  | Configured on part level
Define Characteristic Criteria
|  | Bag |  | Tripura | Completed | 100
3 |  |  | Create Attributes
|  |  | Create Template |  |  |  | Template: CLX Bag Template
|  |  | Define Characteristic Criteria |  |  |  | Configured on part level
|  | Tote Bin |  | Tripura | Completed | 100
4 |  |  | Create Attributes
|  |  | Create Template |  |  |  | Template: CLX Bin Template
|  |  | Define Characteristic Criteria |  |  |  | Configured on part level
|  | Display Components |  | Tripura | Completed | 100
5 |  |  | Create Attributes
|  |  | Create Template |  |  |  | Template: CLX Display Template
|  |  | Define Characteristic Criteria |  |  |  | Configured on part level
6 |  | Cartons |  | Tripura | Completed | 100
Create Attributes
|  |  | Create Template |  |  |  | Template: CLX Carton Template
|  |  | Define Characteristic Criteria |  |  |  | Not Configured
7 |  | Cases |  | Vipin | Completed | 100
|  |  | Create Attributes |  |  |  | Template: CLX-Case-PackagingComponent
|  |  | Create Template |  |  |  | Configured on part level
Define Characteristic Criteria
8 |  | Aerosol Valve |  | Tripura | Completed | 100
Create Attributes
|  |  | Create Template |  |  |  | Template: CLX Aerosol Valve Template
9 |  | Triggers/Finger Pumps |  | Tripura | Completed | 100
|  |  | Create Attributes |  |  |  | Template: CLX Pump Template
Create Template
10 |  | Hardware |  | Tripura | Completed | 100
|  |  | Create Attributes |  |  |  | Template: CLX-Hardware Template
|  |  | Create Template |  |  |  | Characteristic Master/Criteria
Define Characteristic Criteria
11 |  | Pails-Tins |  | Tripura | Completed | 100
|  |  | Create Attributes |  |  |  | Template:
|  |  | Create Template |  |  |  | Characteristic Master/Criteria
Define Characteristic Criteria
12 | Labels | Front Label |  | Vipin | Completed | 100
|  | Back Label | Create Attributes
|  | Neck Label | Create Template |  |  |  | Template: CLX Label
|  |  | Define Characteristic Criteria |  |  |  | Characteristic Master/Criteria
13 |  | Box
14 |  | Cap
15 |  | Bucket Drum Lid
16 |  | Unit Load Packaging
17 |  | Flexible Packaging
18 |  | Instructions/Brochures
19 |  | Miscellaneous
20 |  | Molded Component
21 |  | Partitions |  | Tripura | Completed | 100
Create Attributes
|  |  | Create Template |  |  |  | Template: CLX Partition
|  |  | Define Characteristic Criteria |  |  |  | Characteristic Master/Criteria
22 |  | Package Assemblies
23 |  | Thermoform |  | Tripura | Completed | 100
Create Attributes
|  |  | Create Template |  |  |  | Template: CLX Thermoform
|  |  | Define Characteristic Criteria |  |  |  | Characteristic Master/Criteria
24 |  | Tubes
25 |  | Closures
26 |  | Cans
Substance Spec
27 |  | Consumer Unit
28 |  | Component SubAssembly
29 |  | Customer Unit
30 |  | WIP
31 |  | Inner Packs
32 |  | EmptyWare
33 |  | Raw Materials
34 |  | Resins
35 |  | Formulae
Other Specs
36 |  | Trade Unit Part
Overall %
Create Part With Template
1 | Pallet Pack Components | Full Pallet |  | Vipin | Completed | 100
Create Full Pallet Part
Update Full Pallet Part
|  | Half Pallet |  | Vipin | Completed | 100
Create Half Pallet Part
Update Half Pallet Part
|  | Quarter Pallet |  | Vipin | Completed | 100
Create Quarter Pallet Part
Update Quarter Pallet Part
2 |  | Bottles |  | Vipin | Completed | 100
|  |  | Create Bottle Part |  |  |  | Bottle- Pet
Update Bottle Part
3 |  | Bag |  | Tripura | Completed | 100
|  |  | Create Bag Part |  |  |  | BAG-Plas
Update Bag Part
4 |  | Tote Bin |  | Tripura | Completed | 100
|  |  | Create Tote Bin Part |  |  |  | Tote Bin
Update Tote Bin Part
5 |  | Display Components |  | Tripura | Completed | 100
|  |  | Create Display Part |  |  |  | DISP-BtmFill
Update Display Part
6 |  | Cartons |  | Tripura | Completed | 100
|  |  | Create Carton Part |  |  |  | CTN-Other
Update Carton Part
7 |  | Cases |  | Vipin | Completed | 100
|  |  | Create Case Part |  |  |  | CLX-Case packaging
Update Case Part
8 |  | Aerosol Valve |  | Tripura | Completed | 100
|  |  | Create Aerosol Valve Part |  |  |  | VLV -Aer
Update Aerosol Valve Part
9 |  | Triggers/Finger Pumps |  | Tripura | Completed | 100
|  |  | Create Trigger/Pump Part |  |  |  | CLX Pump
Update Trigger/Pump Part
10 |  | Hardware |  | Tripura | Completed | 100
|  |  | Create Hardware Part |  |  |  | HRDW Br strmFAYP Fltr O-Ring 8J
Update Hardware Part
11 |  | Pails-Tins |  | Tripura | Completed | 100
|  |  | Create Pail Part |  |  |  | TIN -Bottom
Update Pail Part
12 | Labels | Front Label |  | Vipin | Completed | 100
|  | NeckLabel | Create Label Part |  |  |  | CLX-Label for 16fo ft,CLX-Label for 16fo Bk,CLX-Label for 16fo Neck
|  | Back Label | Update Label Part
13 |  | Box
14 |  | Cap
15 |  | Bucket Drum Lid
16 |  | Unit Load Packaging
17 |  | Flexible Packaging
18 |  | Instructions/Brochures
19 |  | Miscellaneous
20 |  | Molded Component
21 |  | Partitions
22 |  | Packaging Assemblies
23 |  | Thermoform
24 |  | Tubes
25 |  | Closures
26 |  | Cans
Substance Spec
27 |  | Consumer Unit
28 |  | Component SubAssembly
29 |  | Customer Unit
30 |  | WIP
31 |  | Inner Packs
32 |  | EmptyWare
33 |  | Raw Materials
34 |  | Resins
35 |  | Formulae
Other Specs
36 |  | Trade Unit Part
Overall %
Create EBOM/FBOM/MBOM
Document Management
Supplier MEP Management
Organization structure Management(Brand/Plants/PLs)
Number Sequence for Parts
Note on C76: Vipin D (Industrial & Engineering Services (I&ES)):These are not present as types hierarchy but template are available , hence added it here.
Note on C158: Vipin D (Industrial & Engineering Services (I&ES)):These are not present as types hierarchy but template are available , hence added it here.

## Integration
S.No | Activity | Tasks WBS | Owner | % Complete | Start Date | End Date | Comments
| PLM Integrations |  |  | 20%
1 | PLM-MDM Integration |  | Rajashekar Rathna
1.1 | Requirements |  |  | 40%
1.1.1 |  | Understand the data to be transferred from PLM to MDM
1.1.2 |  | Understand the data to be transferred back to PLM from MDM
1.1.3 |  | Define the Events to trigger the data transfer from PLM to MDM
1.1.4 |  | Define the Events to trigger the data transfer from MDM to PLM
1.1.5 |  | Identify the Objects, Related Objects to be transferred
1.2 | Design
1.2.1 |  | Analyse the MDM System for supported Integration approaches | Rajashekar Rathna | 80%
1.2.2 |  | Identify the Objects, Related Objects and its attributes in PLM to be transferred
1.2.3 |  | Map the Attributes, Objects, Relationships in PLM and MDM
1.2.4 |  | Finalise the Data format to send and receive from MDM | Rajashekar Rathna | 10%
1.2.5 |  | Check the feasibility and Finalyse the Integration approach (SFTP or REST) | Rajashekar Rathna | 20%
1.2.6 |  | Update Technical Design details with choosen approach and identified attributes based on mapping
1.3 | Development
Develop a REST client to invoke MDM REST service
Fetch alll the Attributes and attach to request as Json/xml
Capture the response and do error handling/logging
1.4 | Unit Testing
2 | PLM-SAP Integration
2.1 | Requirements
2.1.1 |  | Understand the data to be transferred from PLM to SAP |  | 15%
2.1.2 |  | Understand the data to be transferred back to PLM from SAP
2.1.3 |  | Define the Events to trigger the data transfer from PLM to SAP
2.1.3 |  | Define the Events to trigger the data transfer from SAP to PLM
2.1.4 |  | Identify the Objects, Related Objects to be transferred
2.2 | Design
2.2.1 |  | Analyse the OOTB X-BOM Connector for supported Integration approaches and extention |  | 30%
2.2.2 |  | Identify the Objects, Related Objects and its attributes in PLM to be transferred |  | 10%
2.2.3 |  | Map the Attributes, Objects, Relationships in PLM and SAP
2.2.4 |  | Design if customization is needed based on Clorox data model and update technical details
2.2.5 |  | Update Technical Design details with attributes based on mapping and configuration
2.3 | Development
Setup and Configure X-BOM for SAP Connector
Update the config objects with PLM-SAP attributes/relationship mapping for transfer
2.4 | Unit Testing
3 | HP PPM-PLM Integration
3.1 | Requirements |  | Wipro | 70%
Understand the data to be transferred from PLM
Understand the data to be transferred back to PLM
Define the Events to trigger the data transfer from PLM to PPM
Define the Events to trigger the data transfer from PPM to PLM
Identify the Objects, Related Objects to be transferred
3.2 | Design
|  | Analyse the HP PPM for supported Integration approaches and extention | Rajashekar Rathna | 50%
|  | Identify the Objects, Related Objects and its attributes in PLM to be transferred |  | 30%
Map the Attributes, Objects, Relationships in PLM and PPM
Check the feasibility and Finalyse the Integration approach (SFTP or REST)
Update Technical Design details with attributes based on mapping and configuration
3.3 | Development |  |  | 40%
|  | Develop a Scheduled Task to run periodically |  | 100%
|  | Develop a batch file to read upload folder and invoke a MQL/JPO |  | 50%
Develop MQL/JPO to read the files and create projects (Create, Error Log, Failure Handling)
3.4 | Unit Testing
4 | HP MediaBin-PLM Integration
4.1 | Requirements |  | Wipro | 30%
Understand the data to be transferred from PLM
Understand the data to be transferred back to PLM
Define the Events to trigger the data transfer from PLM to MediaBin
Define the Events to trigger the data transfer from MediaBin to PLM
Identify the Objects, Related Objects to be transferred
4.2 | Design
|  | Analyse the HP MediaBin for supported Integration approaches and extention | Rajashekar Rathna | 10%
Identify the Objects, Related Objects and its attributes in PLM to be transferred
Map the Attributes, Objects, Relationships in PLM and MediaBin
Check the feasibility and Finalyse the Integration approach (SFTP or REST)
Update Technical Design details with attributes based on mapping and configuration
4.3 | Development |  |  | 5%
|  | Develop a Scheduled Task to run periodically |  | 100%
Develop a batch file to read upload folder and invoke a MQL/JPO
Develop MQL/JPO to read the files and create projects (Create, Error Log, Failure Handling)
4.4 | Unit Testing

## Testing Task
| Name of Project | Alchemy Release 1
| Environment | Stagging
| Resources | Uma, Bhavya
S.no | Activity/Deliverable | Resource | % of Completion Test case +execution | Expected Start Date | Actual Start Date | Expected End Date | Actual End Date | Comments
Functional TestCases - 34/50
1 | Requirements for testing (FRS is the ref. doc) | PLM Dev Team and Testing | In Progress : 50%
2 | Testing Task list Preparation | Uma | In Progress
3 | Application Walk through for Functionality | Uma, Bhavya | In Progress
4 | Test Case Preparation | Uma, Bhavya | In Progress
4.1 | Project Manager
4.1.1 | Create Project
4.1.2 | Create Project
4.1.3 | Update &Save Project
4.1.4 | LMDM Project Create
4.1.5 | Save Project
4.1.6 | Update &Save Project
4.2 | Consumer Unit Part |  | In Progress
4.2.1 | Create Consumer unit Part
4.2.2 | Create Consumer unit Part
4.2.3 | Save Consumer unit Part
4.2.4 | Update & Save Consumer unit Part
4.2.5 | Check Life Cycle of Consumer Unit Part
4.3 | Trade Unit Part |  | In Progress
4.4.1 | Create Trade unit Part
4.4.2 | Create Trade unit Part
4.4.3 | Save Trade unit Part
4.4.4 | Update & SaveTrade unit Part
4.4.5 | Check Life Cycle of Trade Unit Part
4.4 | Full Pallet |  | In Progress
4.4.1 | Create Full Pallet
4.4.2 | Save Full Pallet
4.4.3 | Update & Save Full Pallet
4.4.4 | Check Life Cycle of Full Pallet
4.5 | Half Pallet
4.5.1 | Create Half Pallet
4.5.2 | Save Half Pallet
4.5.3 | Update & Save Half Pallet
4.5.4 | Check Life Cycle of Half Pallet
4.6 | Quater Pallet Pallet
4.6.1 | Create Quater Pallet
4.6.2 | Save Quater Pallet
4.6.3 | Update & Save Quater Pallet
4.6.4 | Check Life Cycle of Quater Pallet
4.7 | Packaging Component Part |  | Completed
4.7.1 | Create Packaging Component Part |  | Completed
4.7.2 | Save Packaging Component Part |  | Completed
4.7.3 | Update & Save Packaging Component Part |  | Completed
4.7.4 | Check Life Cycle of Packaging Component Part
4.8 | Label Part |  | Completed
4.8.1 | Create Label Part
4.8.2 | Save Label Part
4.8.3 | Update & Save Label Part
4.8.4 | Check Life Cycle of Label Part
4.9 | Closed Part
4.9.1 | Create Closed Part
4.9.2 | Save Closed Part
4.9.3 | Update & Save Closed Part
4.9.4 | Check Life Cycle of Closed Part
4.10 | Formulation Part
4.10.1 | Create Formulation Part
4.10.2 | Save Formulation Part
4.10.3 | Update & Save Formulation Part
4.10.4 | Check Life Cycle of Formulation Part
4.11 | Raw Material Part
4.11.1 | Create Raw Material Part
4.11.2 | Save Raw Material Part
4.11.3 | Update&Save Raw Material Part
4.11.4 | Check Life Cycle of Raw Material Part
4.12 | Substance Part
4.12.1 | Create Substance Part
4.12.2 | Save Substance Part
4.12.3 | Update&Save Substance Part
4.12.4 | Check Life Cycle of Substance Part
4.13 | Supplier Part
4.14.1 | Create Supplier Part
4.14.2 | Save Supplier Part
4.14.3 | Update&Save Supplier Part
4.14.4 | Check Life Cycle of Supplier Part
4.14 | Design BOM
4.14.1 | Create BOMt
4.14.2 | Save BOMt
4.14.3 | Update&Save BOMt
4.14.4 | Check Life Cycle of BOMt
4.15 | Country of Sale
4.12 | Add associated documents to Parts
4.17 | Add associated Image to Parts
4.18 | Revise
4.19 | Specification Templates
4 | Test case Execution
12 | Value Pack
13 | Mixed Pack
Intergration TestCases
1 | MDM
2 | ERP
3 | HP Media Bin

## Data Migration
S.No | Major Tasks | Breakdown Tasks | Phase | Completion% | Assigned to | Planned Start Date | Planned End Date | Comment
1 | Analysis of the WiPDM usage | NA | Requirement | 100 | Inderajith | 2018-12-04 | 2018-12-05 | WiPDM will be needed after XML generation for tranform
2 | Clorox Datamodel Analysis | NA | Requirement | 100 | Sivaranjani | 2018-12-04 | 2018-12-05
3 | Data Modelling | Material & Substance datamodel | Requirement | 50 | Inderajith | 2018-12-05 | 2019-01-31
|  | Part datamodel |  | 30 | Sivaranjani | 2018-12-11 | 2019-01-31
|  | Company-Subsidiary-Plant datamodel |  | 70 | Inderajith | 2018-12-17 | 2019-01-31
4 | Migration Tool Design | NA | Design | 50 | Inderajith | 2018-12-05 | 2019-02-20
5 | Sample Data Analysis for XML template creation | ECM Sample data creation | Design | 40 | Ranjani | 2018-12-24 | 2018-12-25
|  | Specification BOM sample creation |  | 40 | Ranjani | 2018-12-24 | 2018-12-26
|  | XML import template creation for Spec BOM |  | 40 | Ranjani | 2018-12-24 | 2018-12-26
|  | Recipes BOM sample creation |  | 70 | Ranjani | 2018-12-26 | 2018-12-28 | analysis is on going for recipes and ECM.
|  | XML import template creation for Recipe BOM |  | 20 | Ranjani | 2018-12-27 | 2019-01-02 | sample xml generation on going
6 | SAP PDM Extract Analysis | Document extract format analysis | Requirement | 20 | Inderajith/Ranjani | 2018-12-18 | 2019-01-31
|  | Sample data creation |  |  | Inderajith/Ranjani | 2018-12-21 | 2019-01-31
|  | Sample XML creation |  | 100 | Inderajith/Ranjani | 2018-12-04 | 2019-01-31
|  | Specification Extract format |  | 50 | Inderajith/Ranjani | 2018-12-11 | TBD | We have received the sample extraction from krishna for around 11 spec types on 26-Dec-18 analysis is on going.
|  | Recipes Extract format |  | 70 | Inderajith/Ranjani | 2018-12-18 | 2018-12-27 | analysis is on going for recipes and ECM.
|  | ECM Extract format |  | 100 | Inderajith/Ranjani | 2018-12-18 | 2018-12-18
|  | Mapping to 3DX |  |  |  | TBD | TBD
6 | Lotus Notes Raw material data Extract Analysis |  | Requirement
|  | Sample data creation |  |  | Inderajith/Ranjani | 2018-12-21 | 2019-01-31
|  | Sample XML creation |  | 100 | Inderajith/Ranjani | 2018-12-04 | 2019-01-31
|  | Raw material Data Extract format |  | 50 | Inderajith/Ranjani | 2018-12-26 | 2019-01-03 | analysis on going on raw materials.
|  | Mapping to 3DX |  |  | Inderajith/Ranjani | TBD | TBD
7 | Migration Tool Development | Sample XML creation | Development | 100 | Inderajith/Ranjani | 2018-12-04 | 2018-12-07
|  | XML Transform for single data - SAP PDM |  |  | Inderajith/Ranjani | TBD | TBD | Sample xml generation is ongoing for all the data types , once the data model and attributes are finalised we will be starting with Migration tool development.
|  | XML Transform for BOM data - SAP PDM |  |  | Inderajith/Ranjani | TBD | TBD
|  | XML Transform for single raw material data - Lotus |  |  | Inderajith/Ranjani | TBD | TBD
|  | XML Transform for whole raw material data - Lotus |  |  | Inderajith/Ranjani | TBD | TBD
8 | Migration Data Load | SAP PDM Loading - single data | Migration Loading |  | Inderajith/Ranjani | TBD | TBD | Dependency on data extracts and Migration tool development (action item 7) to generate the xml's for data load.
|  | ECM Loading |  |  | Inderajith/Ranjani | TBD | TBD
|  | SAP PDM Loading - BOM data |  |  | Inderajith/Ranjani | TBD | TBD
|  | Raw Data Loading - single data |  |  | Inderajith/Ranjani | TBD | TBD
|  | Raw Data Loading - whole data |  |  | Inderajith/Ranjani | TBD | TBD
9 | Document Migration |  | Migration Loading |  |  |  |  | Dependency on data extracts and Migration tool development (action item 7) to generate the xml's for data load.
|  | Document migration coding |  |  | Inderajith/Ranjani | TBD | TBD
|  | Document Loading |  |  | Inderajith/Ranjani | TBD | TBD
10 | Data Migration Design document | NA | Documentation |  | Inderajith

## Installation
S.No | Major Tasks | Breakdown Tasks | Completion% | Assigned to | Planned Start Date | Planned End Date | Comment
| Sandbox Installation | DB Creation and listener configuration |  | Rajashekar | 15.10.2018 | 18.11.2018
|  | Apache setup |  | Rajashekar | 10.10.2018 | 10.10.2018
|  | Java installation |  | Rajashekar | 20.10.2018 | 26.10.2018
|  | 3DXP GA core services |  | Rajashekar | 26.10.2018 | 02.11.2018
|  | 3DX Mid-market Apps GA |  | Rajashekar | 05.11.2018 | 09.11.2018
|  | 3DX Mid-market Apps FD06 |  | Rajashekar | 12.11.2018 | 16.11.2018
|  | 3dXP FP core services |  | Rajashekar | 19.11.2018 | 23.11.2018
|  | Biovia |  | Rajashekar | 19.11.2018 | 23.11.2018
|  | Engenuity |  | Rajashekar | 19.11.2018 | 23.11.2018
|  | SSO Installation |  | Rajashekar | TBD | TBD
1 | Support Development Installation | DB Creation and listener configuration | 100 | Inderajith | 17.12.2018 | 17.12.2018
|  | Apache setup | 100 | Subhash | 18.12.2018 | 21.12.2018 | issue with TCP port 445, due to this dashboard service is not available
|  | Java installation | 100 | Subhash | 18.12.2018 | 18.12.2018
|  | 3D Passport GA | 100 | Subhash | 18.12.2018 | 18.12.2018
|  | 3D Dashboard GA | 100 | Subhash | 18.12.2018 | 21.12.2018 | re-installed Dashbaord due to port 445 unavailability.
|  | 3D Space GA | 100 | Subhash | 19.12.2018 | 19.12.2018
|  | 3D Swym GA | 100 | Subhash | 18.12.2018 | 18.12.2018
|  | 3D Space Index GA | 100 | Subhash | 18.12.2018 | 18.12.2018
|  | 3D Search GA | 100 | Subhash | 19.12.2018 | 19.12.2018
|  | 3D Swym GA | 100 | Subhash | 18.12.2018 | 18.12.2018
|  | 3D Comment GA | 100 | Subhash | 18.12.2018 | 18.12.2018
|  | 3D Notification GA | 100 | Subhash | 18.12.2018 | 18.12.2018
|  | FCS GA | NA | Subhash | NA | NA
|  | 3DX Mid-market Apps GA: |  | Subhash
|  | 1. ENoviaIPClassificationFoundation | 100 | Subhash | 21.12.2018 | 21.12.2018
|  | 2.EnoviaCollaborativeTasksFoundation | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 3.EnoviaX-CADDesignFoundation | NA | Subhash
|  | 4.EnoviaCollaborationForMicrosoftServer | NA | Subhash
|  | 5.ConnectorsforCatiaV5 | NA | Subhash
|  | 6.EnoviaEnterpriseChangeManagement | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 7.Enovia ProjectManagementFoundation | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 8.EnoviaProgramChangeControlFoundation | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 9.EnoviaProjectExecutionFoundation | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 10.EnoviaEngBOMManagementFoundation | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 11.EnoviaBOMAVLManagement | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 12.EnoviaEnterpriseAVL | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 13.AdapterForX-PDM | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 14.UnifiedCollaborativeDesign | 100 | Subhash | 24.12.2018 | 24.12.2018
|  | 3D Passport FD06 | 100 | Subhash | 20.12.2018 | 20.12.2018
|  | 3D Dashboard FD06 | 100 | Subhash | 20.12.2018 | 21.12.2018 | re-installed Dashbaord due to port 445 unavailability
|  | 3D Space FD06 | 100 | Subhash | 24.12.2018 |  | 24/12/2018: installation in progress. FP failed due to dependencies while executing programs with upgardeDB. trying to fix the issues one by one.
|  | 3D Swym FD06 |  | Subhash
|  | 3D Search FD06 | 100 | Subhash | 20.12.2018 | 20.12.2018
|  | 3D Space Index FD06 |  | Subhash |  |  | FP Failed to install, checking on it.
|  | 3D Comment FD06 | 100 | Subhash | 21.12.2018 | 21.12.2018
|  | 3D Notification FD06 | 100 | Subhash | 20.12.2018 | 20.12.2018
|  | FCS FD06 | NA | Subhash | NA | NA
|  | 3DX Mid-market Apps FD06 | 100 | Subhash | 25.12.2018 | 25.12.2018
|  | 1. ENoviaIPClassificationFoundation 2.EnoviaCollaborativeTasksFoundation 3.EnoviaX-CADDesignFoundation 4.EnoviaCollaborationForMicrosoftServer 5.ConnectorsforCatiaV5 6.EnoviaEnterpriseChangeManagement 7.Enovia ProjectManagementFoundation 8.EnoviaProgramChangeControlFoundation 9.EnoviaProjectExecutionFoundation 10.EnoviaEngBOMManagementFoundation 11.EnoviaBOMAVLManagement 12.EnoviaEnterpriseAVL 13.AdapterForX-PDM 14.UnifiedCollaborativeDesign | 100 | Subhash | 25.12.2018 | 27.12.2018
|  | Biovia |  | Subhash | 02.01.2019 | 04.01.2019
|  | Engenuity |  | Subhash | 07.01.2019 | 07.01.2019
|  | SSO Installation |  | Subhash | TBD | TBD
support QA Installation
2 | Support QA Installation | DB Creation and listener configuration |  | Inderajith | 07.01.2019 | 07.01.2019
|  | Apache setup |  | Subhash | 08.01.2019 | 08.01.2019
|  | Java installation |  | Subhash | 08.01.2019 | 08.01.2019
|  | 3DXP GA core services |  |  | 09.01.2019 | 18.01.2019
|  | 3DX Mid-market Apps GA |  | Subhash | 18.01.2019 | 24.01.2019
|  | 3DX Mid-market Apps FD06 |  | Subhash | 24.01.2019 | 25.01.2019
|  | 3dXP FP core services |  | Subhash | 28.01.2019 | 28.01.2019
|  | Biovia |  | Subhash | 28.01.2019 | 28.01.2019
|  | Engenuity |  | Subhash | 29.01.2018 | 29.01.2018
|  | SSO Installation |  | Subhash | TBD | TBD
Dev Installations
| Dev Installation | DB Creation and listener configuration |  | Inderajith | 29.01.2019 | 29.09.2019
|  | Apache setup |  | Subhash | 30.01.2019 | 30.01.2019
|  | Java installation |  | Subhash | 31.01.2019 | 31.01.2019
|  | 3DXP GA core services |  |  | 04.02.2019 | 08.02.2019
|  | 3DX Mid-market Apps GA |  | Subhash | 11.02.2019 | 15.02.2019
|  | 3DX Mid-market Apps FD06 |  | Subhash | 18.02.2019 | 20.02.2019
3 |  | 3dXP FP core services |  | Subhash | 20.02.2019 | 22.02.2019
4 |  | Biovia |  | Subhash | 25.02.2019 | 25.02.2019
|  | Engenuity |  | Subhash | 26.02.2019 | 27.02.2019
|  | SSO Installation |  | Subhash | TBD | TBD
Staging Installations
| Staging Installation | DB Creation and listener configuration |  | Inderajith | 28.02.2019 | 28.02.2019
|  | Apache setup |  | Subhash | 01.03.2019 | 01.03.2019
|  | Java installation |  | Subhash | 01.03.2019 | 01.03.2019
|  | 3DXP GA core services |  |  | 04.03.2019 | 08.03.2019
|  | 3DX Mid-market Apps GA |  | Subhash | 11.03.2019 | 15.03.2019
|  | 3DX Mid-market Apps FD06 |  | Subhash | 18.03.2019 | 20.03.2019
3 |  | 3dXP FP core services |  | Subhash | 20.03.2019 | 22.03.2019
4 |  | Biovia |  | Subhash | 25.03.2019 | 25.03.2019
|  | Engenuity |  | Subhash | 26.03.2019 | 27.03.2019
|  | SSO Installation |  | Subhash | TBD | TBD
Spinner Installation in Sandbox
Support QA Installation Document

## Miscellaneous
S.No | Tasks | Phase | Completion% | Assigned to | Planned Start Date | Planned End Date | Comment
1 | SSO Analysis | Requirement | 100 | Inderajith | 6.12.2018 | 7.12.2018
2 | Spinners Installation | Requirement | 100 | Inderajith | 11.12.2018 | 12.12.2018
4 | 3DX DB setup for Dev | Installation | 0 | Inderajith | 17.12.2018 | NA